## README
Process Group Roadmap — data template
Fill in the yellow cells. White cells are formulas — leave them alone.
Sheets, in the order to fill them
1. Sprints — your sprint calendar. Add or delete rows to match how far you have actually planned.
2. People — everyone who owns work. Initials become the avatar on the roadmap.
3. ProcessGroups — the workflows being redesigned. One row each. This is the unit of the roadmap.
4. Activities — the bars. One row per piece of work.
5. Milestones — transfers and commitments only. See the list on the Lists sheet.
Rules worth knowing before you start
• Horizon is a property of an ACTIVITY, not of a process group. The same process group can carry
future-state, MVP and PoC work at once — give it one row per activity and set the horizon on each.
• A UX coverage gap is computed by the roadmap, not here: any sprint where a process group has
product-owner activity and no UX activity within plus or minus one sprint.
• A milestone is a transfer or a commitment, never a task finishing. 'Wireframes complete' is not one.
• Design stage is derived from the activity Type — see the mapping on the Lists sheet.
Colour key
Yellow fill = type here. Blue text = a value you typed. Black text = a formula, do not edit.
Grey italic = an example row. Delete the example rows before you use this for real.

## Lists
Horizon | Track | MilestoneType | ActivityType | DesignStage
Future-State Discovery | Product owner | Discovery to backlog | Research | Discover
MVP Delivery | UX | Requirements baselined | Workshop | Discover
Innovation & PoC | Enablement | Design handoff to engineering | Artefact | Define
Operational Enablement |  | Stakeholder demo | Requirements | Define
|  | UAT start | Sign-off | Define
|  | PoC gate decision | Backlog | Define
|  | Graduates to MVP delivery | Framing | Define
|  | Go-live | Concept | Design
|  | Legacy freeze | Design | Design
|  | Steering group | Spike | Design
|  |  | Testing | Validate
|  |  | UAT | Validate
|  |  | Gate | Validate
|  |  | Handoff | Deliver
|  |  | Release | Deliver
|  |  | Provisioning | Deliver
|  |  | Procurement | Enable
|  |  | Access | Enable
|  |  | Recruiting | Enable
Type drives Design stage. Add a pair here to add a stage.

## Sprints
Sprint | Start date | End date | Reduced capacity? | Note
S1 | 2026-09-28 | 2026-10-09 | No
S2 | 2026-10-12 | 2026-10-23 | No
S3 | 2026-10-26 | 2026-11-06 | No
S4 | 2026-11-09 | 2026-11-20 | No
S5 | 2026-11-23 | 2026-12-04 | No
S6 | 2026-12-07 | 2026-12-18 | No
S7 | 2026-12-21 | 2027-01-01 | Yes | Holiday period — plan nothing with a hard commitment here.
S8 | 2027-01-04 | 2027-01-15 | No
S9 | 2027-01-18 | 2027-01-29 | No
S10 | 2027-02-01 | 2027-02-12 | No
S11 | 2027-02-15 | 2027-02-26 | No
S12 | 2027-03-01 | 2027-03-12 | No
S13 | 2027-03-15 | 2027-03-26 | No

## People
Initials | Full name | Role | Team
DW | Dana Whitfield | Product owner | EXAMPLE — delete
TO | Tom Okafor | Researcher | EXAMPLE — delete
LB | Lena Brandt | Designer | EXAMPLE — delete

## ProcessGroups
ID | Process group | Owning product owner | Notes
PG-01 | Work Intake & Triage | Dana Whitfield | EXAMPLE — delete before use

## Activities
Process group ID | Horizon | Track | Activity | Type | Owner | Start sprint | Sprints long | Start date | End date | Design stage
PG-01 | Future-State Discovery | UX | Generative research | Research | Tom Okafor | S1 | 3
PG-01 | MVP Delivery | Product owner | Acceptance criteria | Sign-off | Dana Whitfield | S5 | 2
PG-01 | MVP Delivery | UX | Wireframes | Design | Lena Brandt | S5 | 2

## Milestones
Scope | Process group ID | Sprint | Milestone type | Name | Date
Process group | PG-01 | S4 | Discovery to backlog | Synthesis to 6 backlog items — EXAMPLE

## Summary
Process group | PO activities | UX activities | Total | Milestones | Horizons used
A group with PO activities and no UX activities is where gaps come from.